1. Thursday, May 25- Meeting to review materials, obtain feedback, and next steps.
1. June 2023, work on developing materials.
1. Friday, July 7- Finalize draft materials to share and collect feedback from NEA HQ Cross Team 
1. Monday, July 17 Begin to share with OL School Safety Team to obtain feedback and ends July 31
1. Friday, August 4, Finalize all materials.
1. Monday, August 7 Email materials to participants.
1. Tuesday, August 15, 2023- Test Run, technology, etc.
1. Thursday, August 17, 2023, - Webinar

