- Thursday, May 25- Meeting to review materials, obtain feedback, and next steps.

- June 2023, work on developing materials.

- Friday, July 7- Finalize draft materials to share and collect feedback from NEA HQ Cross Team

- Monday, July 17 Begin to share with OL School Safety Team to obtain feedback and ends July 31

- Friday, August 4, Finalize all materials.

- Monday, August 7 Email materials to participants.

- Tuesday, August 15, 2023- Test Run, technology, etc.

- Thursday, August 17, 2023, - Webinar